## QA Plan
ID | Epic | Persona | User Story | Priority | Preconditions | Test Steps | Expected Result | Status | Tester | Date Tested | Notes
AUTH-01 | Authentication | Anonymous | As a visitor, I want to sign up with email/password so I can start learning. | P0 | Logged out; on /auth?mode=signup | 1. Enter valid username, email, password (8+ chars), confirm password 2. Submit form | Account created; profile exists; redirected; header shows signed-in state | Not Started |  |  | Test duplicate username and weak password errors
AUTH-02 | Authentication | Anonymous | As a visitor, I want to sign up with Google so I can onboard quickly. | P0 | Logged out; on /auth?mode=signup | 1. Click Continue with Google 2. Complete OAuth flow | Account created; profile exists; redirected to intended page | Not Started
AUTH-03 | Authentication | Free user | As a signed-in user, I want to sign in with email/password so I can return to my progress. | P0 | Existing account; logged out | 1. Go to /auth 2. Enter email and password 3. Submit | Signed in; session active; progress available | Not Started
AUTH-04 | Authentication | Free user | As a signed-in user, I want to sign in with Google so I can use OAuth. | P0 | Existing Google-linked account; logged out | 1. Go to /auth 2. Click Continue with Google | Signed in via OAuth; profile loads | Not Started
AUTH-05 | Authentication | Anonymous | As a visitor signing up, I want username validation so I pick a unique handle. | P1 | Logged out; on signup form | 1. Enter taken username 2. Enter invalid characters 3. Enter valid unique username | Errors shown for invalid/taken; valid username accepted | Not Started
AUTH-06 | Authentication | Anonymous | As a visitor, I want email confirmation messaging when required so I know what to do next. | P1 | Email confirmation enabled in Supabase | 1. Sign up with new email 2. Observe post-submit messaging | Clear message to check email; can switch to sign-in mode | Not Started
AUTH-07 | Authentication | Free user | As a signed-in user, I want ?next= redirect after login so I land where I intended. | P0 | Logged out | 1. Visit protected URL e.g. /profile?next preserved via /auth?next=/profile 2. Sign in | Redirected to original destination after auth | Not Started |  |  | Also test from /subscribe and lesson deep links
AUTH-08 | Authentication | Free user | As a signed-in user, I want to sign out from the header menu so my session ends. | P0 | Signed in | 1. Open user account menu 2. Click Sign out | Session cleared; header shows Sign in; protected routes redirect | Not Started
AUTH-09 | Authentication | Free user | As a signed-in user, I want to sign out from Profile so my session ends locally. | P1 | Signed in; on /profile | 1. Click Sign out button on profile | Local session cleared; redirected appropriately | Not Started
AUTH-10 | Authentication | Anonymous | As a visitor, I want protected routes to redirect me to auth so I cannot access gated pages. | P0 | Logged out | 1. Visit /profile 2. Visit /play 3. Visit /play/price-war 4. Visit /play/econ-wordle | /profile and /play/* redirect to auth except Econ Wordle loads | Not Started
AUTH-11 | Authentication | Free user | As a signed-in user, I want my session to persist across page reloads and tabs. | P1 | Signed in | 1. Reload page 2. Open new tab to same site | Session remains active in both contexts | Not Started
AUTH-12 | Authentication | Anonymous | As a visitor, I want a clear error when OAuth fails so I can retry. | P2 | Logged out | 1. Trigger OAuth failure (cancel or misconfigured callback) | Redirect to /auth?error=auth with helpful message | Not Started
NAV-01 | Navigation | Anonymous | As a visitor, I want to browse the landing page so I understand the product. | P1 | Logged out | 1. Visit / 2. Scroll through hero, lessons, games, pricing sections | Page loads; CTAs visible; links work | Not Started
NAV-02 | Navigation | Anonymous | As a visitor, I want to browse the lesson catalog with search/filters so I find content. | P1 | Any | 1. Go to /lessons 2. Search 3. Filter by category/difficulty 4. Paginate | Results update correctly; Lesson Zero shows free; paid lessons show lock for free users | Not Started
NAV-03 | Navigation | Anonymous | As a visitor, I want to view the XP leaderboard so I see community progress. | P2 | Any | 1. Go to /leaderboard | Top users displayed; seeded + real users merged | Not Started
NAV-04 | Navigation | Free user | As a signed-in user, I want header nav (Lessons, Games, Profile) so I can move around. | P0 | Signed in | 1. Click each header nav link | Each destination loads correctly | Not Started
NAV-05 | Navigation | Admin | As an admin, I want an Admin link in the header so I can reach the generator. | P1 | Signed in as admin | 1. Check header for Admin link 2. Click it | Admin link visible; navigates to /admin | Not Started
NAV-06 | Navigation | Anonymous | As a visitor, I want to view pricing on /subscribe so I can compare plans. | P1 | Any | 1. Go to /subscribe | Monthly and lifetime plans displayed with correct pricing | Not Started
LES-01 | Lessons | Anonymous | As a visitor, I want to read Lesson Zero without an account so I can try the format. | P0 | Logged out | 1. Go to /lessons/lesson-zero 2. Read content | Full lesson readable without sign-in | Not Started
LES-02 | Lessons | Free user | As a free user, I want full Lesson Zero access so I get a complete sample. | P0 | Signed in as free user | 1. Open Lesson Zero 2. Navigate all sections | All sections accessible; quizzes available | Not Started
LES-03 | Lessons | Free user | As a free user, I want Section 1 preview on paid lessons so I can evaluate before subscribing. | P0 | Signed in as free user | 1. Open a paid lesson (not Lesson Zero) | Section 1 readable; Section 2+ locked | Not Started
LES-04 | Lessons | Free user | As a free user, I want a subscribe banner after Section 1 preview so I know how to unlock. | P0 | Signed in as free user; on paid lesson Section 1 | 1. Reach end of Section 1 preview | Preview banner with CTA to /subscribe?next=... | Not Started
LES-05 | Lessons | Member | As a member, I want full access to all published lessons so I can complete the curriculum. | P0 | Signed in as member | 1. Open multiple paid lessons 2. Navigate all sections | All sections accessible; no preview lock | Not Started
LES-06 | Lessons | Admin | As an admin, I want full lesson access without paying so I can QA content. | P1 | Signed in as admin (no subscription) | 1. Open paid lesson 2. Navigate all sections | Full access; Generator shortcut visible on editable lessons | Not Started
LES-07 | Lessons | Member | As a member, I want section tabs to unlock progressively so I follow the intended sequence. | P0 | Signed in as member; on lesson with multiple sections | 1. Complete all subsection quizzes in Section 1 2. Check Section 2 tab | Section 2 unlocks; incomplete sections show lock | Not Started
LES-08 | Lessons | Free user | As a free user, I want to be blocked from Section 2+ on paid lessons so preview is enforced. | P0 | Signed in as free user; on paid lesson | 1. Try to access Section 2 tab or content | Section 2+ blocked/disabled | Not Started
QUIZ-01 | Gated Quizzes | Anonymous | As a visitor on Lesson Zero, I want a sign-in prompt on quizzes so I know auth is required. | P0 | Logged out; on Lesson Zero quiz | 1. Scroll to quiz gate | SignInPrompt shown; cannot submit answers | Not Started
QUIZ-02 | Gated Quizzes | Free user | As a free user, I want to submit Lesson Zero quizzes so I can earn XP on the sample. | P0 | Signed in as free user; on Lesson Zero | 1. Answer quiz correctly 2. Submit | Answer accepted; XP awarded; quiz marked complete | Not Started
QUIZ-03 | Gated Quizzes | Free user | As a free user, I want a subscribe prompt on paid-lesson quizzes so I cannot bypass paywall. | P0 | Signed in as free user; on paid lesson Section 1 | 1. Reach quiz on paid lesson | SubscribePrompt shown; cannot submit | Not Started
QUIZ-04 | Gated Quizzes | Member | As a member, I want to answer subsection quizzes so I progress through lessons. | P0 | Signed in as member; on paid lesson | 1. Answer quiz correctly 2. Submit | Answer accepted; progress advances | Not Started
QUIZ-05 | Gated Quizzes | Member | As a member, I want 3 attempts per question so I can learn from mistakes. | P0 | Signed in as member; on quiz question | 1. Answer wrong (attempt 1) 2. Answer wrong (attempt 2) 3. Answer wrong (attempt 3) | Penalties on attempts 1-2; 24h lockout on attempt 3 | Not Started
QUIZ-06 | Gated Quizzes | Member | As a member, I want XP penalties on wrong answers so stakes feel real. | P1 | Signed in as member | 1. Answer quiz wrong once 2. Check profile XP | XP decreases per xpPenalties config; floor at 0 | Not Started
QUIZ-07 | Gated Quizzes | Member | As a member, I want 24h lockout after 3 wrong answers so I cannot brute-force. | P0 | Signed in as member | 1. Fail question 3 times 2. Try to answer again immediately | Locked state shown; 423 on API; gold locked UI | Not Started
QUIZ-08 | Gated Quizzes | Member | As a member, I want to proceed past a locked question so I am not fully blocked. | P1 | Question locked after 3 wrong | 1. Click Next after lockout | Can advance to next subsection despite lock | Not Started
QUIZ-09 | Gated Quizzes | Member | As a member, I want Next disabled until quiz is correct or locked so I cannot skip checks. | P0 | Signed in as member; unanswered quiz | 1. Try clicking Next before answering | Next button disabled until correct or locked | Not Started
QUIZ-10 | Gated Quizzes | Member | As a member, I want no duplicate XP on re-submitting a correct answer. | P1 | Question already answered correctly | 1. Re-submit same correct answer | 409 response; no additional XP | Not Started
QUIZ-11 | Gated Quizzes | Member | As a member, I want the mastery exam unlocked after attempting all section quizzes. | P0 | All section quizzes attempted (not necessarily correct) | 1. Open Mastery tab | Mastery exam available to start | Not Started
QUIZ-12 | Gated Quizzes | Member | As a member, I want a timed mastery exam so retention is tested under pressure. | P1 | Mastery exam unlocked | 1. Start mastery exam 2. Let timer run to zero | Timer counts down; auto-submit at 0:00 | Not Started
QUIZ-13 | Gated Quizzes | Member | As a member, I want mastery pass/fail recorded so lesson completion is accurate. | P0 | Mastery exam completed | 1. Pass exam (70%+) 2. Check lesson progress | masteryPassed set; lesson marked complete; completedAt recorded | Not Started
QUIZ-14 | Gated Quizzes | Free user | As a free user, I want mastery exam blocked so I cannot access paid assessment. | P0 | Signed in as free user; on paid lesson | 1. Try to access Mastery tab | Mastery disabled/blocked | Not Started
XP-01 | XP & Leaderboard | Free user | As a free user, I want XP on correct quiz answers so I feel rewarded. | P0 | Signed in | 1. Answer quiz correctly 2. Check XP display | XP increases by xpReward; toast/update shown | Not Started
XP-02 | XP & Leaderboard | Member | As a member, I want XP penalties that cannot push total below 0. | P1 | Low XP account | 1. Answer multiple questions wrong | XP floors at 0; never negative | Not Started
XP-03 | XP & Leaderboard | Member | As a member, I want level = floor(totalXp/1000)+1 so progression is predictable. | P1 | Known XP total | 1. Check profile level 2. Earn XP to cross 1000 boundary | Level matches formula; level-up at boundary | Not Started
XP-04 | XP & Leaderboard | Member | As a member, I want per-lesson XP shown in lesson sidebar so I track lesson progress. | P1 | On lesson with quizzes | 1. Earn XP in lesson 2. Check sidebar | Per-lesson XP earned updates; completion rings accurate | Not Started
XP-05 | XP & Leaderboard | Member | As a member, I want profile Progress tab to show level bar and XP to next level. | P1 | Signed in as member | 1. Go to /profile?tab=progress | Level bar, XP to next level, activity shown | Not Started
XP-06 | XP & Leaderboard | Anonymous | As a visitor, I want to view the public leaderboard so I see top learners. | P2 | Any | 1. Go to /leaderboard | Top 50 displayed; usernames and XP visible | Not Started
XP-07 | XP & Leaderboard | Member | As a member, I want my rank on profile so I know where I stand. | P2 | Signed in with XP | 1. Check profile Progress tab rank | Rank displayed and reasonable vs leaderboard | Not Started
XP-08 | XP & Leaderboard | Member | As a member, I want level-up when crossing 1000 XP boundary mid-quiz. | P2 | Near level boundary | 1. Earn XP pushing past 1000 2. Observe UI | Level increments; UI reflects new level | Not Started
PATH-01 | Personalization | Free user | As a free user, I want path setup onboarding so I get a tailored sequence. | P0 | Signed in; path not set up | 1. Trigger PathSetupModal 2. Answer ~6 questions 3. Complete flow | Path saved; Profile Path tab shows ordered lessons; tagline shown | Not Started
PATH-02 | Personalization | Free user | As a free user, I want to skip path setup so I am not forced immediately. | P1 | Path setup modal open | 1. Click Skip | Modal closes; needsPathSetup remains; banner persists | Not Started
PATH-03 | Personalization | Member | As a member, I want my path ordered by interests so lessons feel relevant. | P0 | Path setup completed | 1. Review Profile Path tab order | Lessons ordered by interest weights; relevant topics first | Not Started
PATH-04 | Personalization | Member | As a member, I want a path tagline so personalization is visible. | P1 | Path setup completed | 1. Check path section tagline | Tagline reflects primary interest e.g. policy focus | Not Started
PATH-05 | Personalization | Member | As a member, I want path items marked completed/in_progress/up_next/locked/coming_soon. | P0 | Path with mixed lesson states | 1. Review path timeline and list | Each item shows correct state badge | Not Started
PATH-06 | Personalization | Free user | As a free user, I want non-Lesson Zero path items locked so paywall is clear. | P0 | Signed in as free user; path set up | 1. Review path items | Only Lesson Zero accessible; others locked | Not Started
PATH-07 | Personalization | Member | As a member, I want Change focus to retake onboarding so I can update interests. | P1 | Path already set up | 1. Profile Path → Change focus 2. New answers → save | Path reorders; preferences overwritten; tagline updates | Not Started
PATH-08 | Personalization | Free user | As a free user, I want a path setup banner on /lessons until I complete or skip. | P1 | needsPathSetup true | 1. Visit /lessons | Banner prompts path setup | Not Started
PATH-09 | Personalization | Member | As a member, I want Continue on your path card so I resume easily. | P1 | Path set up with next lesson | 1. Visit /lessons or dashboard | Continue card links to next path lesson | Not Started
PATH-10 | Personalization | Member | As a member, I want unpublished lessons as coming soon on my path. | P2 | Path includes unpublished lessons | 1. Review path list | Unpublished items show coming soon state | Not Started
PROF-01 | Profile | Free user | As a signed-in user, I want to view my profile so I see my identity and progress. | P0 | Signed in | 1. Go to /profile | Profile loads with username, avatar, tabs | Not Started
PROF-02 | Profile | Free user | As a signed-in user, I want to change my username so I can personalize my account. | P1 | Signed in | 1. Profile Personal tab → change username → save | Username updates; uniqueness validated | Not Started
PROF-03 | Profile | Free user | As a signed-in user, I want an avatar (generated or Google) so my profile feels personal. | P2 | Signed in | 1. Check avatar on profile and header | Avatar displays correctly for auth method | Not Started
PROF-04 | Profile | Member | As a member, I want Profile tabs via ?tab= deep links. | P1 | Signed in as member | 1. Visit /profile?tab=path 2. ?tab=subscription 3. ?tab=progress | Correct tab opens for each deep link | Not Started
PROF-05 | Profile | Member | As a member, I want Progress tab with completed lessons, heatmap, streak. | P1 | Member with lesson activity | 1. Open Progress tab | Completed lessons, heatmap, streak days shown | Not Started
PROF-06 | Profile | Member | As a member, I want Subscription tab showing plan status. | P0 | Active subscription | 1. Open Subscription tab | Plan type, status, manage billing CTA shown | Not Started
PROF-07 | Profile | Lapsed member | As a lapsed subscriber, I want subscription status to reflect canceled/past_due. | P0 | Canceled or past_due subscription | 1. Open Subscription tab 2. Try paid lesson access | Status shows lapsed; lesson access revoked | Not Started
BILL-01 | Billing | Anonymous | As a visitor, I want to view plans on /subscribe. | P1 | Any | 1. Go to /subscribe | Monthly and lifetime plans with pricing displayed | Not Started
BILL-02 | Billing | Free user | As a free user, I want checkout to require auth so billing is tied to my account. | P0 | Logged out | 1. Go to /subscribe 2. Click subscribe on a plan | Redirected to /auth?next=... | Not Started
BILL-03 | Billing | Free user | As a free user, I want Stripe checkout for monthly/lifetime so I can subscribe. | P0 | Signed in as free user; Stripe test mode | 1. Select plan 2. Complete Stripe test checkout | Subscription active; member access unlocked | Not Started
BILL-04 | Billing | Free user | As a free user, I want ?next= preserved through checkout so I return to intended lesson. | P0 | On paid lesson preview | 1. Click subscribe CTA with next param 2. Complete checkout | Returned to original lesson with full access | Not Started
BILL-05 | Billing | Member | As a member, I want immediate lesson access after successful payment. | P0 | Just completed checkout | 1. Return from Stripe 2. Open previously locked lesson | Full lesson access without manual refresh delay | Not Started |  |  | Note webhook timing edge case
BILL-06 | Billing | Member | As a member, I want Stripe billing portal to manage/cancel subscription. | P1 | Active subscription | 1. Profile Subscription → Manage billing 2. Open portal | Stripe portal loads; can view/cancel plan | Not Started
BILL-07 | Billing | Free user | As a free user, I want canceled checkout to return gracefully. | P2 | In Stripe checkout | 1. Cancel/back out of checkout | Return to site with ?canceled=1; no broken state | Not Started
BILL-08 | Billing | Lapsed member | As a lapsed subscriber, I want lesson access revoked after cancellation. | P0 | Subscription canceled | 1. Open paid lesson 2. Try quiz submit | Preview mode restored; SubscribePrompt on quizzes | Not Started
WORD-01 | Econ Wordle | Anonymous | As a visitor, I want to play today's Wordle without an account. | P0 | Logged out | 1. Go to /play/econ-wordle | Game loads; no auth redirect | Not Started
WORD-02 | Econ Wordle | Anonymous | As a visitor, I want 6 guesses and on-screen keyboard. | P0 | On Wordle page | 1. Type guesses via keyboard 2. Submit up to 6 times | Guesses accepted; keyboard highlights correct/present/absent | Not Started
WORD-03 | Econ Wordle | Anonymous | As a visitor, I want local streak/progress persisted in browser. | P1 | Played at least one game | 1. Reload page 2. Check streak/progress | Local storage retains progress and streak | Not Started
WORD-04 | Econ Wordle | Anonymous | As a visitor, I want hints after N guesses. | P2 | Multiple wrong guesses | 1. Continue guessing until hint threshold | Hint unlocks; word length may reveal | Not Started
WORD-05 | Econ Wordle | Anonymous | As a visitor, I want term + definition on finish. | P1 | Game won or lost | 1. Complete puzzle | Term and definition displayed on finish screen | Not Started
WORD-06 | Econ Wordle | Anonymous | As a visitor, I want Learn this term lesson link. | P1 | Game finished | 1. Click lesson link on finish screen | Navigates to related lesson | Not Started
WORD-07 | Econ Wordle | Anonymous | As a visitor, I want emoji share grid. | P2 | Game finished | 1. Click share 2. Copy grid | Emoji result grid copied to clipboard | Not Started
WORD-08 | Econ Wordle | Admin | As an admin, I want debug affordances on Wordle if applicable. | P3 | Signed in as admin | 1. Play Wordle as admin | Admin-only debug UI visible if implemented | Not Started
MGN-01 | Margin | Anonymous | As a visitor, I want /play to require auth so Margin is account-gated. | P0 | Logged out | 1. Visit /play | Redirect to auth | Not Started
MGN-02 | Margin | Free user | As a free user, I want the Games hub listing Wordle + Margin. | P0 | Signed in | 1. Go to /play | Games catalog shows Econ Wordle and Margin cards | Not Started
MGN-03 | Margin | Free user | As a free user, I want the tutorial vs Prof. Aldo so I learn rules. | P0 | Signed in as free user | 1. Go to /play/price-war/tutorial 2. Complete tutorial flow | Tutorial match runs; coach guidance shown; can submit moves | Not Started
MGN-04 | Margin | Free user | As a free user, I want vs-bot matches so I can practice solo. | P0 | Signed in as free user | 1. Lobby → Play vs bot 2. Play through match | Bot match created; full flow works to post-match | Not Started
MGN-05 | Margin | Free user | As a free user, I want Rapid 15-min mode so I can play timed matches. | P0 | Signed in as free user | 1. Select Rapid 15+0 2. Queue or play | Rapid mode available and playable | Not Started |  |  | Verify against product spec: Rapid free, Blitz paid
MGN-06 | Margin | Free user | As a free user, I want Blitz 5-min blocked so fast mode is member-only. | P0 | Signed in as free user | 1. Try to select/play Blitz 5+0 | Blitz blocked with 403 or UI lock | Not Started
MGN-07 | Margin | Member | As a member, I want Blitz 5-min mode so I can play fast games. | P0 | Signed in as member | 1. Select Blitz 5+0 2. Queue and play | Blitz available and playable | Not Started
MGN-08 | Margin | Free user | As a free user, I want only 1 concurrent match so caps are enforced. | P0 | Free user with match in progress | 1. Start second match while first active | Second match blocked with cap error message | Not Started
MGN-09 | Margin | Member | As a member, I want up to 5 concurrent matches. | P1 | Signed in as member | 1. Start multiple matches (up to 5) | Up to 5 concurrent; 6th blocked | Not Started
MGN-10 | Margin | Free/Member | As a player, I want full match flow: lobby → briefing → decide → review → waiting → report → continue. | P0 | Signed in | 1. Start match 2. Play full round cycle through post-match | All phases work; URLs sync with server phase | Not Started
MGN-11 | Margin | Free/Member | As a player, I want legal moves enforced so invalid actions are rejected. | P1 | In decide phase | 1. Attempt invalid move combinations | Only legal moves selectable; API rejects illegal submits | Not Started
MGN-12 | Margin | Free/Member | As a player, I want round reports showing economic outcomes. | P1 | Match in progress | 1. Complete a round 2. View report | Economic metrics and outcomes displayed per round | Not Started
MGN-13 | Margin | Free/Member | As a player, I want post-match summary with outcome. | P0 | Match completed | 1. Reach post-match screen | Winner/loser, key stats, play again CTA shown | Not Started
MGN-14 | Margin | Member | As a member, I want rated/Elo matches when MARGIN_RATED_ENABLED is on. | P1 | Rated flag enabled; member account | 1. Play ranked queue match 2. Check rating delta | Elo/rating updates on post-match | Not Started
MGN-15 | Margin | Free user | As a free user, I want unrated messaging when rated is enabled. | P2 | Rated flag on; free account | 1. Play Rapid match as free user | Unrated label/message shown appropriately | Not Started
MGN-16 | Margin | Free/Member | As a player, I want timeout forfeit when clock runs out. | P1 | Match with low clock | 1. Let clock expire without submitting | Forfeit/timeout outcome; match ends | Not Started
MGN-17 | Margin | Free/Member | As a player, I want inactivity forfeit after idle rounds. | P2 | Match in progress | 1. Skip activity for configured idle rounds | Inactivity forfeit triggered | Not Started
MGN-18 | Margin | Free/Member | As a player, I want bankruptcy terminal screen when applicable. | P1 | Match leading to bankruptcy | 1. Play until bankruptcy condition | Bankruptcy screen shown; match terminal | Not Started
MGN-19 | Margin | Free/Member | As a player, I want abandoned match handling when opponent leaves. | P1 | PvP match | 1. Opponent abandons or disconnects | Abandoned outcome handled gracefully | Not Started
MGN-20 | Margin | Free/Member | As a player, I want mid-match refresh to recover to correct phase. | P1 | Match in progress | 1. Refresh browser mid-match | Loading gate then correct phase URL restored | Not Started
MGN-21 | Margin | Free user | As a free user, I want template-only post-match coach debrief. | P1 | Free user; match completed | 1. View post-match coach section | Template debrief shown; no LLM coach | Not Started
MGN-22 | Margin | Member | As a member, I want AI coach debrief when LLM is available. | P1 | Member; OpenRouter configured | 1. Complete match 2. View coach debrief | LLM-generated personalized debrief shown | Not Started
MGN-23 | Margin | Free/Member | As a player, I want recommended lessons after match. | P1 | Match completed | 1. Check post-match recommended lessons | Lesson links shown; Start lesson navigates correctly | Not Started
MGN-24 | Margin | Free/Member | As a player, I want match history listing past games. | P1 | At least one completed match | 1. Go to /play/price-war/history | Past matches listed with outcomes and dates | Not Started
MGN-25 | Margin | Member | As a member, I want Margin leaderboard when rated is on. | P2 | Rated enabled | 1. Go to /play/price-war/leaderboard | Rankings displayed | Not Started
MGN-26 | Margin | Free/Member | As a player, I want notifications page for match events. | P2 | Match events occurred | 1. Go to /play/price-war/notifications | Notifications listed | Not Started
ADM-01 | Admin | Admin | As an admin, I want access to /admin lesson generator. | P1 | Signed in as admin | 1. Go to /admin | Admin dashboard loads with lesson generator | Not Started
ADM-02 | Admin | Non-admin | As a non-admin, I want admin routes blocked. | P1 | Signed in as free/member (not admin) | 1. Visit /admin | Redirect with admin_forbidden error | Not Started
ADM-03 | Admin | Admin | As an admin, I want the lesson pipeline Sources through Publish. | P2 | Admin access; test lesson | 1. Walk pipeline tabs 2. Generate/preview content | Each tab functional; preview uses LessonPlayer | Not Started
ADM-04 | Admin | Admin | As an admin, I want Margin admin: matches, players, costs, move catalog. | P2 | Signed in as admin | 1. Visit /admin/pricewar 2. Check each section | Match traces, player search, costs, move catalog load | Not Started
ADM-05 | Admin | Admin | As an admin, I want Generator shortcut on editable lessons. | P3 | Admin on lesson page | 1. Open lesson as admin | Generator link visible and navigates to editor | Not Started
X-01 | Cross-cutting | All | As a user, I want mobile-responsive lesson tabs and quiz UI. | P1 | Mobile viewport or device | 1. Open lesson on mobile 2. Navigate tabs and quizzes | Tabs scroll; quiz stacks; usable on small screens | Not Started
X-02 | Cross-cutting | All | As a user, I want mobile-responsive Margin screens. | P1 | Mobile viewport | 1. Play Margin match on mobile | All phases usable; loading gates work | Not Started
X-03 | Cross-cutting | All | As a user, I want Margin disabled gracefully when PRICEWAR_ENABLED=false. | P2 | Feature flag off | 1. Try to access /play/price-war | Redirect to /lessons?notice=pricewar_disabled or 503 | Not Started
X-04 | Cross-cutting | Member | As a member, I want lesson SEO/metadata on public pages. | P3 | Any | 1. View page source on lesson page | Title, meta, JSON-LD present | Not Started
X-05 | Cross-cutting | Free user | As a free user, I want Wordle to lesson bridge working end-to-end. | P1 | Wordle completed | 1. Click Learn this term link 2. Complete lesson flow | Navigation works; lesson loads correctly | Not Started
X-06 | Cross-cutting | Member | As a member, I want game to recommended lesson bridge end-to-end. | P1 | Match completed | 1. Click recommended lesson from post-match 2. Start lesson | Lesson opens; progress tracked | Not Started

## Reference
Test Personas
Anonymous | No account — public browsing, Wordle, Lesson Zero read
Free user | Signed up, no subscription
Member | Active monthly or lifetime subscription
Member (monthly) | Active monthly Stripe subscription
Member (lifetime) | Active lifetime subscription
Lapsed member | Canceled or past_due subscription
Admin | Email in ADMIN_EMAILS env var
Non-admin | Signed-in user without admin email
Free/Member | Applies to both free and paid players
All | Any persona including anonymous
Status Values
Not Started | Test case not yet run
In Progress | Currently being tested
Pass | All expected results met
Fail | Bug found or expected result not met
Blocked | Cannot test — dependency or environment issue
Skipped | Intentionally not tested this cycle
Priority
P0 | Smoke / release blocker — must pass
P1 | Important — should pass before release
P2 | Nice to have — test if time allows
P3 | Low priority / admin-only